## 0325
Status Report for Team 6 - FlowTrack
Project |  |  |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-25 |  |  |  | Overall Status: | Yellow
Contact: | Thuc Luong |  |  |  | Explanation: | The API keys and tokens taking longer to work through is slowing us down a little bit, but we are still able to work around it and focus on setting up the rest of the application.
Prepared By: | Thuc Luong
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Vivian Chen | Database connection, set up api connections & link tokens. Started frontend development.
Ly Ha | Set up DB, created Wireframes, set up api tokens.
Tavonga Tafuma | Started on UserController, TransactionController, StatementController, and UserController.
Thuc Luong | Created the DAOs and DTOs necessary for the application
ID # | Key Issues | Action Plan |  |  |  |  | Status
1 | Taking a little longer to set up API keys and tokens. | Research and two team members working on it instead of one to debug and move forward. |  |  |  |  | Yellow
None
None
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Flowcharts, UML, ERD completed |  |  | Green | 2025-03-21 | 100%
File Structure Setup |  |  | Green | 2025-03-24 | 100%
Completed DB Schema |  |  | Green | 2025-03-24 | 100%
Connect to API (i.e. connection, tokens) |  |  | Green | 2025-03-25 | 100%
Track Transaction |  |  | Red | 2025-03-26 | 0
Financial Statements |  |  | Red | 2025-03-26 | 0%
Frontend |  |  | Green | 2025-03-27 | 15%
Stretch Goal: Forecast Finances |  |  | Green | 2025-03-27 | 0%
Presentation |  |  | Green | 2025-03-27 | 10%
Green
Green
Green

## 0326
Status Report for Team 6 - FlowTrack
Project |  |  |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-26 |  |  |  | Overall Status: | Green
Contact: | Tavonga Tafuma |  |  |  | Explanation: | We have resolved all key issues and are now on target for deadlines.
Prepared By: | Tavonga Tafuma
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Vivian Chen | Transaction, Account, and Item Endpoints. Plaid Link Connection.
Ly Ha | Frontend Development for Login, Register. Logic and Register Logic in middleware. Plaid Link Connection.
Thuc Luong | Setup the service layer interface and implementation for Users and Statements.
Tavonga Tafuma | Started on forecast finances.
ID # | Key Issues | Action Plan |  |  |  |  | Status
1 | Taking a little longer to set up API keys and tokens. | Research and two team members working on it instead of one to debug and move forward. |  |  |  |  | Handled: The issue was pulling all the tokens and connecting all the tokens to handling the plaid link. Plaid link is UI service to get users information, resolved by reading api documentation and debugging.
None
None
None
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Flowcharts, UML, ERD completed |  |  | Green | 2025-03-21 | 100%
File Structure Setup |  |  | Green | 2025-03-24 | 100%
Completed DB Schema |  |  | Green | 2025-03-24 | 100%
Connect to API (i.e. connection, tokens) |  |  | Green | 2025-03-25 | 100%
Track Transaction |  |  | Green | 2025-03-26 | 70%
Financial Statements |  |  | Green | 2025-03-26 | 10%
Frontend |  |  | Green | 2025-03-27 | 25%
Stretch Goal: Forecast Finances |  |  | Green | 2025-03-27 | 25%
Presentation |  |  | Green | 2025-03-27 | 50%
Green
Green
Green

## 0327
Status Report for Team 6 - FlowTrack
Project |  |  |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-27 |  |  |  | Overall Status: | Green
Contact: | Ly Ha |  |  |  | Explanation: | We have resolved all key issues and are now on target for deadlines.
Prepared By: | Ly Ha
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Vivian Chen | Setting up Frontend (Landing Page, Login, Register)
Ly Ha | Finished Frontend for Tracking Transactions and transaction filtering.
Thuc Luong | Created the financial statement functionality, Worked on the sandbox test user.
Tavonga Tafuma | Created the frontend for forecast spending and the implementation for forecast spending.
ID # | Key Issues | Action Plan |  |  |  |  | Status
1 | Taking a little longer to set up API keys and tokens. | Research and two team members working on it instead of one to debug and move forward. |  |  |  |  | Handled: The issue was pulling all the tokens and connecting all the tokens to handling the plaid link. Plaid link is UI service to get users information, resolved by reading api documentation and debugging.
None
None
None
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Flowcharts, UML, ERD completed |  |  | Green | 2025-03-21 | 100%
File Structure Setup |  |  | Green | 2025-03-24 | 100%
Completed DB Schema |  |  | Green | 2025-03-24 | 100%
Connect to API (i.e. connection, tokens) |  |  | Green | 2025-03-25 | 100%
Track Transaction |  |  | Green | 2025-03-26 | 100%
Financial Statements |  |  | Yellow | 2025-03-26 | 90%
Frontend |  |  | Green | 2025-03-27 | 50%
Stretch Goal: Forecast Finances |  |  | Green | 2025-03-27 | 90%
Presentation |  |  | Green | 2025-03-27 | 50%
Green
Green
Green

## 0328
Status Report for Team 6 - FlowTrack
Project |  |  |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-28 |  |  |  | Overall Status: | Green
Contact: | Vivian Chen |  |  |  | Explanation: | We have resolved all key issues and are focusing on refactoring and improving frontend development.
Prepared By: | Vivian Chen
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Vivian Chen | Statement Views, refactoring code and fixed bugs throughout frontend
Ly Ha | Frontend development. Added printing statements as a PDFs. Transaction frontend logic.
Thuc Luong | Worked on the presentation and test cases for the service layer
Tavonga Tafuma | Unit testing for DAOs, completion of slideshow, bug fixing throughout backend.
ID # | Key Issues | Action Plan |  |  |  |  | Status
1 | Taking a little longer to set up API keys and tokens. | Research and two team members working on it instead of one to debug and move forward. |  |  |  |  | Handled: The issue was pulling all the tokens and connecting all the tokens to handling the plaid link. Plaid link is UI service to get users information, resolved by reading api documentation and debugging.
None
None
None
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Flowcharts, UML, ERD completed |  |  | Green | 2025-03-21 | 100%
File Structure Setup |  |  | Green | 2025-03-24 | 100%
Completed DB Schema |  |  | Green | 2025-03-24 | 100%
Connect to API (i.e. connection, tokens) |  |  | Green | 2025-03-25 | 100%
Track Transaction |  |  | Green | 2025-03-26 | 100%
Financial Statements |  |  | Green | 2025-03-26 | 100%
Frontend |  |  | Green | 2025-03-28 | 95%
Stretch Goal: Forecast Finances |  |  | Green | 2025-03-27 | 100%
Presentation |  |  | Green | 2025-03-27 | 100%
Green
Green
Green