## Status Report
Status Report for Team #6 FlowTrack
Project |  | Status: (Red/Yellow/Green)
Date: | 2025-03-25 | Overall Status: | Yellow
Contact: | Thuc Luong | Explanation: | The API keys and tokens taking longer to work through is slowing us down a little bit but we are still able to work around it and focus on setting up the rest of the application.
Prepared By: | Thuc Luong
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Vivian Chen | Database connection, set up api connections & link tokens. Started frontend development.
Ly Ha | Set up DB, created Wireframes, set up api tokens.
Tavonga Tafuma | Started on UserController, TransactionController, StatementController, and UserController. Finished with set up.
Thuc Luong | Created the DAOs and DTOs necessary for the application
ID # | Key Issues | Action Plan |  |  | Status
1 | Taking a little longer to set up API keys and tokens. | Research and two team members working on it instead of one to debug and move forward. |  |  | Yellow
Critical Milestones |  | Health | Due Date | Comment/Status %
Flowcharts, UML, ERD completed |  | Green | 2025-03-21 | 100%
File Structure Setup |  | Green | 2025-03-24 | 100%
Completed DB Schema |  | Green | 2025-03-24 | 100%
Connect to API (i.e. connection, tokens) |  | Green | 2025-03-25 | 100%
Track Transaction |  | Red | 2025-03-26 | 15%
Financial Statements |  | Red | 2025-03-26 | 0%
Frontend |  | Green | 2025-03-27 | 25%
Stretch Goal: Forecast Finances |  | Green | 2025-03-27 | 0%
Presentation |  | Green | 2025-03-27 | 10%
Green