## 0327
Status Report for Team 6 - FlowTrack
Project |  |  |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-27 |  |  |  | Overall Status: | Green
Contact: | Ly Ha |  |  |  | Explanation: | We have resolved all key issues and are now on target for deadlines.
Prepared By: | Ly Ha
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Vivian Chen | Setting up Frontend (Landing Page, Login, Register)
Ly Ha | Finished Frontend for Tracking Transactions and transaction filtering.
Thuc Luong | Created the financial statement functionality, Worked on the sandbox test user.
Tavonga Tafuma | Created the frontend for forecast spending and the implementation for forecast spending.
ID # | Key Issues | Action Plan |  |  |  |  | Status
1 | Taking a little longer to set up API keys and tokens. | Research and two team members working on it instead of one to debug and move forward. |  |  |  |  | Handled: The issue was pulling all the tokens and connecting all the tokens to handling the plaid link. Plaid link is UI service to get users information, resolved by reading api documentation and debugging.
None
None
None
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Flowcharts, UML, ERD completed |  |  | Green | 2025-03-21 | 100%
File Structure Setup |  |  | Green | 2025-03-24 | 100%
Completed DB Schema |  |  | Green | 2025-03-24 | 100%
Connect to API (i.e. connection, tokens) |  |  | Green | 2025-03-25 | 100%
Track Transaction |  |  | Green | 2025-03-26 | 100%
Financial Statements |  |  | Yellow | 2025-03-26 | 90%
Frontend |  |  | Green | 2025-03-27 | 50%
Stretch Goal: Forecast Finances |  |  | Green | 2025-03-27 | 90%
Presentation |  |  | Green | 2025-03-27 | 50%
Green
Green
Green